## Sprint 1
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As an authorized user, I would like to login so that I can save my cart and preferences. | 1. Learn about PostgreSQL 2. Research how to properly store accounts in a database 3. Prototype UI | Environment creation and knowledge acquisition | F, KA | 4 | 4 | 1-2: Adam 65% Liam 35% 3: Ashley 60% Liam 30% Aaron 10%
2 | As a user, I would like to be able to filter through items in a search so that I can more efficiently find an item I am looking for. | 1. Learn about PostgreSQL 2. Research how to properly store items in a database 3. Prototype UI | Environment creation and knowledge acquisition | F, KA | 4 | 4 | 1-2: Adam 65% Liam 35% 3: Ashley 60% Liam 30% Aaron 10%
3 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1. Learn about notifications 2. Decide on suitable notification timeout | Notification System | KA | 3 | 1 | Adam: 100%
4 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1. Learn about Java location libraries 2. Prototype UI for tracking | Tracking System | KA | 6 | ~0.5 | Adam: 100%

## Sprint 2
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
30 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1) Setup item cart database 2) Connect to item cart database 3) Setup email notification system | Notification System | F | 4 | 0 | 1: N/A 2: N/A 3: N/A
62 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1) Choose location API 2) Figure out tracking API | Tracking System | KA | 2 | 2 | 1-2: Adam Green
1 | As an unauthorized user, I would like to create an account so that I can save my preferences across devices and platforms. | 1) Setup account register page 2) Connect to user database 3) Create new user in user database | Accounts and Login | F | 4 | 3 | 1: N/A 2: Adam 75%, Liam 25% 3: Adam 100%
2 | As an authorized user, I would like to login to my account so that I can save my cart and preferences. | 1) Setup login page 2) Connect to user database 3) Authenticate user credentials | Databases and User Authentication + Profiles | F | 3 | 2 | 1: Ashley 100% 2: Adam 50%, Liam 50% 3: N/A
3 | As an authorized user, I would like to logout of my account so that my privacy and safety can remain intact. | 1) Setup logout button | Databases & User Authentication + Profiles | F | 1 | 1 | 1: Ashley 100%
4 | As an authorized user, I would like to be able to logout of my account at once on all devices so that my privacy and safety can remain intact. | 1) Setup logout page | Databases & User Authentication + Profiles | F | 1 | 0 | 1: N/A
5 | As an administrator, I would like to be able to ban accounts that go against our terms of service so that Centauri can remain safe and secure for its users. | 1) Connect to user database 2) Remove user from database | Databases & User Authentication + Profiles | F | 2 | 2 | 1-2: Adam 100%
6 | As an administrator, I would like to be able to delete all items for a seller who has broken our terms of service so that Centauri can remain safe and secure for its users. | 1) Connect to user database table | Databases & User Authentication + Profiles | F | 2 | 2 | 1: Adam: 100%
7 | As an authorized user, I would like a “Forgot your password/account details” option to send this information to my email address so that I can change my password in the event that I forget it. | 1) Setup "Forgot your password/account details" button 2) Connect to user database 3) Set up email notification system | Databases & User Authentication + Profiles | F | 2 | 2 | 1: Ashley 100% 2: Adam: 100% 3: N/A
8 | As an authorized user, I would like to be able to make changes to my account settings so that I can keep my information up to date. | 1) Connect to user database 2) Set up user settings page 3) Create settings button | Databases & User Authentication + Profiles | F | 2 | 1.5 | 1: Adam 100% 2: N/A 3: Adam 100%
9 | As an authorized user, I would like the application to not tell the person utilizing the “Forgot your password/account details” button if there exists an account with the specified email address, so that a hacker cannot trace my account through my email. | 1) Setup "Forgot your password/account details" button 2) Setup email has been sent page | Databases & User Authentication + Profiles | F | 2 | 1 | 1: Ashley: 100% 2: N/A
10 | As a business owner, I would like to modify my profile so that I can appeal and advertise to customers. | 1) Setup business profile page 2) Connect to user database 3) Modify business profile within database | Databases & User Authentication + Profiles | F | 3 | 1 | 1: N/A 2: Adam 50%, Liam 50% 3: N/A
11 | As a business owner, I would like to associate my email address with both a business account and a personal account so that I can maintain privacy. | 1) Connect to user database 2) Create new user with business setting enabled | Databases & User Authentication + Profiles | F | 2 | 1 | 1: Adam 50%, Liam 50% 2: N/A

## Sprint 3
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
12 | As an authorized user, I need to be able to delete my payment method so that my privacy and safety can remain intact. | 1. Research how to store payment methods (credit card) | Payment Methods table creation | KA | 2 | 1 | 1. Adam: 100%
13 | As a user, I want to see the list of available items for purchase so that I can purchase these items from Centauri vendors. | 1. Setup item table 2. Connect to item table 3. Display list of available items | Item table creation | F, T | 3 | 2 | 1. Adam: 70% Liam: 30% 2. Adam: 100% 3. Adam: 100%
14 | As a business owner, I want to be able to see a list of bids on a particular item I have posted so that I can keep up to date with my merchandise. | 1. Setup item table 2. Return a specific item from the table 3. Display the attributes of the item including bids | Item table creation | F, T | 4 | 2 | 1. Adam: 70% Liam: 30% 2. Adam: 100% 3. N/A
15 | As an authorized user, I would like to be able to initiate a refund so that I can get my money back for unsatisfactory service. | 1. Set up Purchase History table 2. Connect to Purchase History table 3. Set up Refund button 4. Set up Refund page | Purchase History table creation | F, T | 6 | 0 | N/A
16 | As a user, I would like my payment method and credentials to not be disclosed to the seller so that I can maintain security and privacy. | 1. Setup payment methods table 2. Connect to payment methods table 3. Create boolean for access to payment methods | Payment Methods table creation | T | 6 | 0 | N/A
17 | As a user, I would like to be able to add an item to my cart so that I can remember a specific item for later. | 1. Setup cart table 2. Add an item to the table | Cart table creation | T | 1 | 0 | N/A
18 | As a user, I would like to be able to remove an item from my cart so that my cart does not become cluttered with unwanted items. | 1. Setup cart table 2. Delete an item from the table | Cart table creation | T | 1 | 0 | N/A
19 | As a user, I would like to be able to see a list of items in my cart so that I can buy these items at a later date. | 1. Setup cart table 2. Display the items in the cart table | Cart table creation | F, T | 3 | 0 | N/A
20 | As an authorized user, I would like to save my payment method so that I can complete transactions quicker. | 1. Setup payment methods table 2. Access payment methods table | Payment Methods table creation | T | 5 | 0 | N/A
21 | As a user, I would like to see the quality of an item, for example whether it is new, used, or digital (with books, games, etc.) so that I can see what options are best for me. | 1. Setup item table 2. Link quality id to item | Item table creation | F, T | 2 | 2 | 1. Adam: 70% Liam: 30% 2. Adam: 100%
22 | As a seller, I would like to be able to specify whether the object will be allowed to be bid on or bought out, or both (but not neither) so that I can make decisions for the sale of my item based on its demand. | 1. Setup item table 2. Add booleans for selling types | Item table creation | F, T | 2 | 2 | 1. Adam: 70% Liam: 30% 2. Adam: 25% Liam: 75%
23 | As a seller, I would like to be able to specify the minimum increment for bids so that people don’t overcut by pennies. | 1. Setup item table 2. Set minimum increment for bids as a column in the table | Item table creation | T | 1 | 0.5 | 1. Adam: 70% Liam: 30% 2. N/A
24 | As a premium account owner, I would like to be able to have a recurring subscription so that I can pay for my premium account conveniently. | 1. Add premium user boolean to Users table 2. Develop Subscriptions Table to track user subscriptions 3. Connect Subscription table with Users table | Premium Users, Subscriptions Table creation | F | 3 | 0 | N/A
25 | As a premium account owner, I would like to be able to choose faster shipping times so that I can receive my package in the quickest way possible. | 1. Add premium user boolean to Users table 2. Construct Items table 3. Figure out how to store shipping options by item properly | Items table creation, Premium Users, Finalizing User login | F, KA | 2 | 0 | N/A
26 | As an authorized user, I would like to be able to see a history of all items I have viewed so that I can leave reviews on previous items. | 1. Store item ids of previously viewed items in user table | User table creation | T | 3 | 0 | N/A
27 | As an authorized user, I would like to be able to initiate a return so that I can send back an item that doesn’t meet my expectations. | 1. Develop purchase history mechanism - table with one to one relationship on userid 2. Construct purchase history table | Return button creation, Item table creation | F | 2 | 0 | N/A
28 | As a user, I would like to see the quantity of an item that a seller is selling so that I know whether or not it is pertinent to buy this item at the present time. | 1. Setup item table 2. Connect to item table 3. Display number of items | Item table creation | F | 2 | 2 | 1. Adam: 70% Liam: 30% 2. Adam: 100% 3. Adam: 100%
29 | As a user, I would like to be notified when I have been outbid on an item so that I can know to rebid on this item or walk away. | 1. Construct items table 2. Add bids array as column (treat as stack) | Item table creation | F | 3 | 1 | 1. Adam: 70% Liam: 30% 2. N/A
31 | As a user, I would like to be able to opt out of email notifications so that I do not receive unwanted emails. | 1. Set up Settings page 2. Set up Email Notifications toggle 3. Connect to User database | User Profiles, Email System | F | 2 | 1 | 1. Aaron: 100% 2. N/A 3. Adam: 100%
32 | As a user, I would like to be able to add multiple shipping addresses and choose between them at checkout so that I can conveniently choose the appropriate address. | 1. Construct Addresses table 2. Connect to Addresses table 3. Add to Addresses table | Address Table creation | T | 2 | 1 | 1. Adam: 100% 2. Adam: 100% 3. N/A
33 | As a user, I want to be able to see the reviews of an item so that I know if an item is exactly what I am looking for. | 1. Construct Reviews table 2. Connect to Reviews table 3. Set up Reviews UI 4. Display list of Reviews | Item table creation | F, T | 3 | 0 | N/A
34 | As a user, I want to be able to see the reputation of a store so that I know what vendors are credible. | 1. Set up Business Profile Page 2. Set up Vendor Rating view | User profiles and business accounts | F | 4 | 0 | N/A
30 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1. Set up item cart database 2. Connect to item cart database 3. Set up email notification system | Item Cart Table, Email system | F | 2 | 0 | N/A
62 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1. Set up order tracking table (1 userid to many order tracking entries) | User Profiles | T, KA | 1 | 0 | N/A
1 | As an unauthorized user, I would like to create an account so that I can save my preferences across devices and platforms. | 1. Set up user table | User Profiles | T | 1 | 1 | 1: Adam: 100%
2 | As an authorized user, I would like to login to my account so that I can save my cart and preferences. | 1. Set up login screen 2. Set up cart table | Item cart table creation, User profiles | F, T | 2 | 1 | 1. Ashley: 50% Adam: 50% 2. N/A
3 | As an authorized user, I would like to logout of my account so that my privacy and safety can remain intact. | 1. Set up logout button 2. Remove user from current user logged in device | Logout button UI | F | 2 | 1 | 1. Ashley: 100%
4 | As an authorized user, I would like to be able to logout of my account at once on all devices so that my privacy and safety can remain intact. | 1. Remove current user logged in any device | Accounts & Logout | F | 1 | 0 | N/A
5 | As an administrator, I would like to be able to ban accounts that go against our terms of service so that Centauri can remain safe and secure for its users. | 1. Develop administrator database commands (in flask api) 2. Add banned boolean in users table | User Profiles | F, T | 3 | 0 | N/A
6 | As an administrator, I would like to be able to delete all items for a seller who has broken our terms of service so that Centauri can remain safe and secure for its users. | 1. Develop administrator database commands (in flask api) 2. Add banned boolean in businesses table | User Profiles | F, T | 3 | 0 | N/A
7 | As an authorized user, I would like a “Forgot your password/account details” option to send this information to my email address so that I can change my password in the event that I forget it. | 1. Develop layout of Forgot your password page 2. Research email Java system 3. Send user email if exists | Email System | F, T, KA | 3 | 2 | 1. Aaron: 75% Ashley: 25% 2. Adam: 100% 3. N/A
8 | As an authorized user, I would like to be able to make changes to my account settings so that I can keep my information up to date. | 1. Develop UI for user settings | User profiles | F | 1 | 1 | 1. Aaron: 100%
9 | {DEPRECATED} As an authorized user, I would like the application to not tell the person utilizing the “Forgot your password/account details” button if there exists an account with the specified email address, so that a hacker cannot trace my account through my email. | 1. Set up user table | User profiles | T | 1 | 1 | 1. Adam: 70% Liam: 30%
10 | As a business owner, I would like to modify my profile so that I can appeal and advertise to customers. | 1. Research modular layouts in android 2. Figure out how to store modular business pages in java | User profiles and business accounts | KA | 1 | 0 | N/A
11 | As a business owner, I would like to associate my email address with both a business account and a personal account so that I can maintain privacy. | 1. Develop businesses database 2. Construct businesses database 3. Figure out method for business to create business account in application | User profiles and business accounts | T, KA | 3 | 1 | 1. Adam: 50% Liam: 50% 2-3. N/A

## Sprint 4
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
35 | As a premium account owner, I would like to be able to cancel my subscription so that I do not keep paying for a service I do not require. | 1. Connect users table and subscriptions table with foreign key 2. Populate subscriptions table columns 3. Create user profile UI in Android 4. Create UX for user profiles | Connect Tables, Profile UI | F, T | 2 | 2 | 1. Adam: 100% 2. Adam: 100% 3: Lak: 50% Adam: 50% 4: Adam 100%
36 | As a premium account owner, I would like to be able to change the payment details of my subscription (differ from payment method for general use) so that I can use the most convenient form of payment for me. | 1. Research how to store payment methods | Payment System | KA | 2 | 0 | N/A
37 | As an authorized user, I would like to be able to leave a review for an item so that future buyers know my opinions on the item. | 1. Diagram reviews table 2. Setup reviews table | Reviews Table Set Up | T | 2 | 1 | 1. Adam: 100% 2: N/A
38 | As an authorized user, I would like to be able to leave a review for a business so that future buyers know my opinions on the business. | 1. Diagram reviews table 2. Setup reviews table | Reviews Table Set Up | T | 2 | 1 | 1. Adam: 100% 2: N/A
39 | As an authorized user, I would like to be able to contact Centauri Inc. regarding a purchase, in the case that the business owner is not compliant so that I can be fully satisfied with my purchasing experience. | 1. Model customer service page in Android 2. Create UX for customer service page | Customer Service UI | F | 2 | 0 | N/A
40 | As an authorized user, I would like to be able to contact Centauri Inc. regarding a purchase, in the case that the business owner does not respond so that I can be fully satisfied with my purchasing experience. | 1. Model customer service page in Android 2. Create UX for customer service page | Customer Service UI | F | 2 | 0 | N/A
41 | As an administrator, I would like the ability to monitor chat logs at the discretion of the buyer/seller to be able to deal with harassment or extortion on either side so that Centauri can make informed decisions on penalties associated with the reported behavior. | 1. Figure out how to create chats between users in app | Chat System | KA | 2 | 0 | N/A
42 | As a business owner, I want to see my store’s listed items so that I know what needs to be in stock. | 1. Model business profile UI in Android 2. Create UX for business profiles | Profiles UI | F | 2 | 2 | 1. Aaron: 100% 2. Adam: 100%
43 | As an authorized user, I would like to be able to stop a purchase and have a full refund before the item is sent so that I can have flexibility in case I change my mind about a purchase. | 1. Research how to store payment methods | Payment System | KA | 2 | 0 | N/A
44 | As an authorized user, I would like to be able to erase the history of all items I have viewed so that my privacy and safety can remain intact. | 1. Research purchase history | Purchase History Table Creation | KA | 3 | 0 | N/A
45 | As an authorized user, I would like to be able to contact the business owner regarding my purchase so that I can make special requests for the item. | 1. Figure out how to create chats between users in app | Chat System | KA | 2 | 0 | N/A
46 | As a user, I would like to be able to add two-factor authentication to my account to ensure the safety and security of my account. | 1. Research 2FA | Authentication System | KA | 6 | 0 | N/A
47 | As a business owner, I want to be able to see the reviews for my store so that I can know how to improve my business. | 1. Create UI mock up for reviews page 2. Create reviews page 3. Add UX for reviews page | Reviews UI | F | 2 | 0.5 | 1. Ashley: 100% 2. N/A 3. N/A
12 | As an authorized user, I need to be able to delete my payment method so that my privacy and safety can remain intact. | 1. Research how to store payment methods | Payment System | KA | 1 | 0 | N/A
13 | As a user, I want to see the list of available items for purchase so that I can purchase these items from Centauri vendors. | 1. Create main item listing page in Android 2. Add UX for listing page | Item Listing UI | F, T | 3 | 1.5 | 1. Adam: 50% Ashley: 50%
14 | As a business owner, I want to be able to see a list of bids on a particular item I have posted so that I can keep up to date with my merchandise. | 1. Create Bids table 2. Diagram bid/buy logistics for purchasing | Bids Table Creation | T | 2 | 2 | 1. Adam: 100% 2. Adam: 100%
15 | As an authorized user, I would like to be able to initiate a refund so that I can get my money back for unsatisfactory service. | 1. Set up Purchase History table 2. Connect to Purchase History table 3. Set up Refund button 4. Set up Refund page | Purchase Table Creation, Refunds UI | F, T | 3 | 0 | N/A
16 | As a user, I would like my payment method and credentials to not be disclosed to the seller so that I can maintain security and privacy. | 1. Research how to store payment methods | Payment System | KA | 1 | 0 | N/A
17 | As a user, I would like to be able to add an item to my cart so that I can remember a specific item for later. | 1. Populate orders table with columns 2. Create API endpoints for orders table | Improve Orders Table | T | 3 | 1.5 | 1. Adam: 100%
18 | As a user, I would like to be able to remove an item from my cart so that my cart does not become cluttered with unwanted items. | 1. Connect Orders table to Order Items table 2. Create API endpoint to remove an item from Order Items | Improve Orders Table | T | 3 | 1.5 | 2. Adam: 100%
19 | As a user, I would like to be able to see a list of items in my cart so that I can buy these items at a later date. | 1. Connect Orders table to Order Items table 2. Create API endpoint to show all Order Items | Improve Orders Table | T | 3 | 1.5 | 2. Adam: 100%
20 | As an authorized user, I would like to save my payment method so that I can complete transactions quicker. | 1. Research how to store payment methods | Payment System | KA | 1 | 0 | N/A
21 | As a user, I would like to see the quality of an item, for example whether it is new, used, or digital (with books, games, etc.) so that I can see what options are best for me. | 1. Setup Quality enum in Items table | Improve Items Table | T | 1 | 0 | N/A
22 | As a seller, I would like to be able to specify whether the object will be allowed to be bid on or bought out, or both (but not neither) so that I can make decisions for the sale of my item based on its demand. | 1. Create Bids table 2. Diagram bid/buy logistics for purchasing | Bids Table Creation | T | 2 | 2 | 1. Adam: 100% 2. Adam: 100%
23 | As a seller, I would like to be able to specify the minimum increment for bids so that people don’t overcut by pennies. | 1. Create Bids table 2. Diagram bid/buy logistics for purchasing | Bids Table Creation | T | 2 | 2 | 1. Adam: 100% 2. Adam: 100%
24 | As a premium account owner, I would like to be able to have a recurring subscription so that I can pay for my premium account conveniently. | 1. Connect users table and subscriptions table with foreign key 2. Populate subscriptions table columns | Connect Tables | T | 3 | 1 | 1: Adam 100%
25 | As a premium account owner, I would like to be able to choose faster shipping times so that I can receive my package in the quickest way possible. | 1. Connect users table and subscriptions table with foreign key 2. Populate subscriptions table columns | Connect Tables | T | 3 | 1 | 1: Adam 100%
26 | As an authorized user, I would like to be able to see a history of all items I have viewed so that I can leave reviews on previous items. | 1. Setup View History table | View History Table Creation | T | 1 | 0 | N/A
27 | As an authorized user, I would like to be able to initiate a return so that I can send back an item that doesn’t meet my expectations. | 1. Diagram Purchase History table 2. Setup Purchase history table 3. Populate Purchase History table with dummy data to test | Purchase History Table Creation | T | 3 | 2 | 1. Adam: 100% 2. Adam: 100%
28 | As a user, I would like to see the quantity of an item that a seller is selling so that I know whether or not it is pertinent to buy this item at the present time. | 1. Model items page in Android | Items UI | F | 2 | 1 | 1. Ashley: 100%
29 | As a user, I would like to be notified when I have been outbid on an item so that I can know to rebid on this item or walk away. | 1. Send email notification to user when their bid is superseded | Notifications System | T | 2 | 0 | N/A
31 | As a user, I would like to be able to opt out of email notifications so that I do not receive unwanted emails. | 1. Discuss table structure for subscription callbacks to send emails | Subscriptions Table | NF | 1 | 0 | N/A
32 | As a user, I would like to be able to add multiple shipping addresses and choose between them at checkout so that I can conveniently choose the appropriate address. | 1. Figure out workaround to store multiple addresses in users table | Improve Users Table | KA | 1 | 1 | 1. Aaron: 100%
33 | As a user, I want to be able to see the reviews of an item so that I know if an item is exactly what I am looking for. | 1. Diagram Reviews table 2. Setup Reviews table | Reviews Table Set Up | T | 2 | 2 | 1. Aaron 100% 2. Adam: 100%
34 | As a user, I want to be able to see the reputation of a store so that I know what vendors are credible. | 1. Model business profile UI in Android 2. Create UX for business profiles | Profiles UI | F | 2 | 2 | 1. Aaron 100% 2. Adam: 100%
30 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1. Send email notification to user at certain time threshold 2. Discuss table structure for subscription callbacks to send emails | Notifications System | T, NF | 3 | 0 | N/A
62 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1. Complete orders table | Orders Table Completion | T | 1 | 1 | 1. Adam: 100%
3 | As an authorized user, I would like to logout of my account so that my privacy and safety can remain intact. | 1. Create Sessions table to maintain user account sessions 2. Create API endpoint to logout of my current session | Sessions Table Creation | T | 2 | 1 | 1. Adam: 100% 2. N/A
4 | As an authorized user, I would like to be able to logout of my account at once on all devices so that my privacy and safety can remain intact. | 1. Create Sessions table to maintain user account sessions 2. Create API endpoint to logout all sessions | Sessions Table Creation | T | 2 | 1 | 1. Adam: 100% 2. N/A
5 | As an administrator, I would like to be able to ban accounts that go against our terms of service so that Centauri can remain safe and secure for its users. | 1. Model user profile UI in Android 2. Create UX for user profiles | Profiles UI | F | 2 | 2 | 1. Aaron: 100% 2. N/A
6 | As an administrator, I would like to be able to delete all items for a seller who has broken our terms of service so that Centauri can remain safe and secure for its users. | 1. Model business profile UI in Android 2. Create UX for business profiles | Profiles UI | F | 2 | 2 | 1. Aaron 100% 2. Adam: 100%
7 | As an authorized user, I would like a “Forgot your password/account details” option to send this information to my email address so that I can change my password in the event that I forget it. | 1. Send email notification to user with code 2. Create UI intent to send user to next forgot password page to enter code | Notifications System | F | 3 | 3 | 1. Adam: 100% 2. Adam: 50% Ashley: 50%
8 | As an authorized user, I would like to be able to make changes to my account settings so that I can keep my information up to date. | 1. Model Settings page in Android Studio | Settings UI | F | 1 | 1 | 1. Aaron: 75% Ashley: 25%
10 | As a business owner, I would like to modify my profile so that I can appeal and advertise to customers. | 1. Model business profile in Android Studio | Profiles UI | F | 1 | 1 | 1. Aaron: 100%
11 | As a business owner, I would like to associate my email address with both a business account and a personal account so that I can maintain privacy. | 1. Diagram businesses table 2. Setup businesses table | Businesses Table Set Up | T | 2 | 2 | 1. Adam: 100% 2. Adam: 100%

## Sprint 5
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
18 | As a user, I would like to be able to send my chat logs to Centauri Inc. to have sellers penalized for harassment or extortion so that I can feel safe using Centauri as a platform. |  |  |  | 2
19 | As a user, I would like my conversations to be encrypted/protected, so that malicious users cannot trace me. |  |  |  | 2
20 | As a business owner, I would like my conversations to be encrypted/protected, so that malicious users cannot trace me. |  |  |  | 2
35 | As a user, I would like to see recommended items similar to previous purchases or viewed items so that I can quickly purchase similar items to what I have bought in the past. |  |  |  | 30 (unknown)
36 | As a user, I would like to have different options of contact when contacting Customer service(chat/call/email) so that if one option is unreliable at the current time, I can fall back on another option. |  |  |  | 1
37 | As a user, I would like to be able to sort items in a search based on ratings so that I can view only the most credential items. |  |  |  | 3
38 | As a user, I would like to be able to sort items in a search based on price so that I can view items within my price range. |  |  |  | 3
39 | As a user, I would like to be able to see my previous orders so that I can write recommendations for future buyers. |  |  |  | 2
40 | As a user, I would like to be able to see a list of the items that I have bids on so that I can be informed of if and when I have won a bid. |  |  |  | 3
41 | As a user, I would like to be able to filter through items in a search so that I can more efficiently find an item I am looking for. |  |  |  | 3
42 | As a business owner, I would like to be able to send my chat logs to Centauri Inc. to have buyers penalized for harassment so that I can feel safe using Centauri as a platform. |  |  |  | 3
60 | As a user, I would like to be able to redeem a gift card for in store credit so that I can purchase items using these methods. |  |  |  | 5
61 | As a user, I would like to be able to purchase a gift card so that I can send it to another Centauri user. |  |  |  | 3

## Sprint 6
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
21 | As a user, I want to be able to access a user manual regarding the application, so that I don't get lost in its use. |  |  |  | 6

## Sprint 7
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage