## Product Backlog
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As an unauthorized user, I would like to create an account so that I can save my preferences across devices and platforms. | 2 | H | W | 4
2 | As an authorized user, I would like to login to my account so that I can save my cart and preferences. | 2 | H | W | 3
3 | As an authorized user, I would like to logout of my account so that my privacy and safety can remain intact. | 2 | H | W | 2
4 | As an authorized user, I would like to be able to logout of my account at once on all devices so that my privacy and safety can remain intact. | 2 | H | W | 4
5 | As an administrator, I would like to be able to ban accounts that go against our terms of service so that Centauri can remain safe and secure for its users. | 2 | H | W | 1
6 | As an administrator, I would like to be able to delete all items for a seller who has broken our terms of service so that Centauri can remain safe and secure for its users. | 2 | H | W | 1
7 | As an authorized user, I would like a “Forgot your password/account details” option to send this information to my email address so that I can change my password in the event that I forget it. | 2 | H | W | 1
8 | As an authorized user, I need to be able to delete my payment method so that my privacy and safety can remain intact. | 3 | H | W | 1
9 | As a user, I want to see the list of available items for purchase so that I can purchase these items from Centauri vendors. | 3 | H | W | 4
10 | As a business owner, I want to be able to see a list of bids on a particular item I have posted so that I can keep up to date with my merchandise. | 3 | H | W | 2
11 | As an authorized user, I would like to be able to initiate a refund so that I can get my money back for unsatisfactory service. | 3 | H | W | 6
12 | As a user, I would like my payment method and credentials to not be disclosed to the seller so that I can maintain security and privacy. | 3 | H | W | 1
13 | As a user, I would like to be able to add an item to my cart so that I can remember a specific item for later. | 3 | H | W | 1
14 | As a user, I would like to be able to remove an item from my cart so that my cart does not become cluttered with unwanted items. | 3 | H | W | 1
15 | As a user, I would like to be able to see a list of items in my cart so that I can buy these items at a later date. | 3 | H | W | 2
16 | As a premium account owner, I would like to be able to cancel my subscription so that I do not keep paying for a service I do not require. | 4 | H | W | 2
17 | As a premium account owner, I would like to be able to change the payment details of my subscription (differ from payment method for general use) so that I can use the most convenient form of payment for me. | 4 | H | W | 2
18 | As a user, I would like to be able to send my chat logs to Centauri Inc. to have sellers penalized for harassment or extortion so that I can feel safe using Centauri as a platform. | 5 | H | W | 2
19 | As a user, I would like my conversations to be encrypted/protected, so that malicious users cannot trace me. | 5 | H | W | 2
20 | As a business owner, I would like my conversations to be encrypted/protected, so that malicious users cannot trace me. | 5 | H | W | 2
21 | As a user, I want to be able to access a user manual regarding the application, so that I don't get lost in its use. | 6 | H | W | 6
22 | As an authorized user, I would like to be able to make changes to my account settings so that I can keep my information up to date. | 2 | M | W | 1
23 | As an authorized user, I would like to save my payment method so that I can complete transactions quicker. | 3 | M | W | 2
24 | As a user, I would like to see the quality of an item, for example whether it is new, used, or digital (with books, games, etc.) so that I can see what options are best for me. | 3 | M | W | 1
25 | As a seller, I would like to be able to specify whether the object will be allowed to be bid on or bought out, or both (but not neither) so that I can make decisions for the sale of my item based on its demand. | 3 | M | W | 2
26 | As a seller, I would like to be able to specify the minimum increment for bids so that people don’t overcut by pennies. | 3 | M | W | 2
27 | As a premium account owner, I would like to be able to have a recurring subscription so that I can pay for my premium account conveniently. | 3 | M | W | 3
28 | As a premium account owner, I would like to be able to choose faster shipping times so that I can receive my package in the quickest way possible. | 3 | M | W | 1
29 | As an authorized user, I would like to be able to leave a review for an item so that future buyers know my opinions on the item. | 4 | M | W | 2
30 | As an authorized user, I would like to be able to leave a review for a business so that future buyers know my opinions on the business. | 4 | M | W | 2
31 | As an authorized user, I would like to be able to contact Centauri Inc. regarding a purchase, in the case that the business owner is not compliant so that I can be fully satisfied with my purchasing experience. | 4 | M | W | 2
32 | As an authorized user, I would like to be able to contact Centauri Inc. regarding a purchase, in the case that the business owner does not respond so that I can be fully satisfied with my purchasing experience. | 4 | M | W | 2
33 | As an administrator, I would like the ability to monitor chat logs at the discretion of the buyer/seller to be able to deal with harassment or extortion on either side so that Centauri can make informed decisions on penalties associated with the reported behavior. | 4 | M | W | 2
34 | As a business owner, I want to see my store’s listed items so that I know what needs to be in stock. | 4 | M | W | 2
35 | As a user, I would like to see recommended items similar to previous purchases or viewed items so that I can quickly purchase similar items to what I have bought in the past. | 5 | M | W | 30 (unknown)
36 | As a user, I would like to have different options of contact when contacting Customer service(chat/call/email) so that if one option is unreliable at the current time, I can fall back on another option. | 5 | M | W | 1
37 | As a user, I would like to be able to sort items in a search based on ratings so that I can view only the most credential items. | 5 | M | W | 3
38 | As a user, I would like to be able to sort items in a search based on price so that I can view items within my price range. | 5 | M | W | 3
39 | As a user, I would like to be able to see my previous orders so that I can write recommendations for future buyers. | 5 | M | W | 2
40 | As a user, I would like to be able to see a list of the items that I have bids on so that I can be informed of if and when I have won a bid. | 5 | M | W | 3
41 | As a user, I would like to be able to filter through items in a search so that I can more efficiently find an item I am looking for. | 5 | M | W | 3
42 | As a business owner, I would like to be able to send my chat logs to Centauri Inc. to have buyers penalized for harassment so that I can feel safe using Centauri as a platform. | 5 | M | W | 3
43 | As an authorized user, I would like the application to not tell the person utilizing the “Forgot your password/account details” button if there exists an account with the specified email address, so that a hacker cannot trace my account through my email. | 2 | L | W | 1
44 | As an authorized user, I want to be able to change my settings easily so that I can keep my account up to date in a timely fashion. | 2 | L | W | 3
45 | As a business owner, I would like to modify my profile so that I can appeal and advertise to customers. | 2 | L | W | 3
46 | As a business owner, I would like to associate my email address with both a business account and a personal account so that I can maintain privacy. | 2 | L | W | 1
47 | As an authorized user, I would like to be able to see a history of all items I have viewed so that I can leave reviews on previous items. | 3 | L | W | 4
48 | As an authorized user, I would like to be able to initiate a return so that I can send back an item that doesn’t meet my expectations. | 3 | L | W | 4
49 | As a user, I would like to see the quantity of an item that a seller is selling so that I know whether or not it is pertinent to buy this item at the present time. | 3 | L | W | 2
50 | As a user, I would like to be notified when I have been outbid on an item so that I can know to rebid on this item or walk away. | 3 | L | W | 4
51 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 3 | L | W | 4
52 | As a user, I would like to be able to opt out of email notifications so that I do not receive unwanted emails. | 3 | L | W | 1
53 | As a user, I would like to be able to add multiple shipping addresses and choose between them at checkout so that I can conveniently choose the appropriate address. | 3 | L | W | 2
54 | As a user, I want to be able to see the reviews of an item so that I know if an item is exactly what I am looking for. | 3 | L | W | 2
55 | As a user, I want to be able to see the reputation of a store so that I know what vendors are credible. | 3 | L | W | 1
56 | As an authorized user, I would like to be able to stop a purchase and have a full refund before the item is sent so that I can have flexibility in case I change my mind about a purchase. | 4 | L | W | 2
57 | As an authorized user, I would like to be able to erase the history of all items I have viewed so that my privacy and safety can remain intact. | 4 | L | W | 3
58 | As an authorized user, I would like to be able to contact the business owner regarding my purchase so that I can make special requests for the item. | 4 | L | W | 2
59 | As a user, I would like to be able to add two-factor authentication to my account to ensure the safety and security of my account. | 4 | L | W | 6
60 | As a business owner, I want to be able to see the reviews for my store so that I can know how to improve my business. | 4 | L | W | 2
61 | As a user, I would like to be able to redeem a gift card for in store credit so that I can purchase items using these methods. | 5 | L | W | 5
62 | As a user, I would like to be able to purchase a gift card so that I can send it to another Centauri user. | 5 | L | W | 3
63 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 6 | L | W | 8