## Sprint 1
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As an authorized user, I would like to login so that I can save my cart and preferences. | 1. Learn about PostgreSQL 2. Research how to properly store accounts in a database 3. Prototype UI | Environment creation and knowledge acquisition | F, KA | 4 | 4 | 1-2: Adam 65% Liam 35% 3: Ashley 60% Liam 30% Aaron 10%
2 | As a user, I would like to be able to filter through items in a search so that I can more efficiently find an item I am looking for. | 1. Learn about PostgreSQL 2. Research how to properly store items in a database 3. Prototype UI | Environment creation and knowledge acquisition | F, KA | 4 | 4 | 1-2: Adam 65% Liam 35% 3: Ashley 60% Liam 30% Aaron 10%
3 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1. Learn about notifications 2. Decide on suitable notification timeout | Notification System | KA | 3 | 1 | Adam: 100%
4 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1. Learn about Java location libraries 2. Prototype UI for tracking | Tracking System | KA | 6 | ~0.5 | Adam: 100%

## Copy of Sprint i
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage