## Sprint 2
ID | User Story | Story Tasks | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
50 | As a user, I would like to be notified of when an item in my cart is selling out so that I can purchase that item before it runs out. | 1) Setup item cart database 2) Connect to item cart database 3) Setup email notification system | Notification System | F | 4 | 0 | 1: N/A 2: N/A 3: N/A
62 | As an authorized user, I would like to be able to track my order status so that I can make arrangements for a package’s arrival. | 1) Choose location API 2) Figure out tracking API | Tracking System | KA | 2 | 2 | 1-2: Adam Green
1 | As an unauthorized user, I would like to create an account so that I can save my preferences across devices and platforms. | 1) Setup account register page 2) Connect to user database 3) Create new user in user database | Accounts and Login | F | 4 | 3 | 1: N/A 2: Adam 75%, Liam 25% 3: Adam 100%
2 | As an authorized user, I would like to login to my account so that I can save my cart and preferences. | 1) Setup login page 2) Connect to user database 3) Authenticate user credentials | Databases and User Authentication + Profiles | F | 3 | 2 | 1: Ashley 100% 2: Adam 50%, Liam 50% 3: N/A
3 | As an authorized user, I would like to logout of my account so that my privacy and safety can remain intact. | 1) Setup logout button | Databases & User Authentication + Profiles | F | 1 | 1 | 1: Ashley 100%
4 | As an authorized user, I would like to be able to logout of my account at once on all devices so that my privacy and safety can remain intact. | 1) Setup logout page | Databases & User Authentication + Profiles | F | 1 | 0 | 1: N/A
5 | As an administrator, I would like to be able to ban accounts that go against our terms of service so that Centauri can remain safe and secure for its users. | 1) Connect to user database 2) Remove user from database | Databases & User Authentication + Profiles | F | 2 | 2 | 1-2: Adam 100%
6 | As an administrator, I would like to be able to delete all items for a seller who has broken our terms of service so that Centauri can remain safe and secure for its users. | 1) Connect to user database table | Databases & User Authentication + Profiles | F | 2 | 2 | 1: Adam: 100%
7 | As an authorized user, I would like a “Forgot your password/account details” option to send this information to my email address so that I can change my password in the event that I forget it. | 1) Setup "Forgot your password/account details" button 2) Connect to user database 3) Set up email notification system | Databases & User Authentication + Profiles | F | 2 | 2 | 1: Ashley 100% 2: Adam: 100% 3: N/A
22 | As an authorized user, I would like to be able to make changes to my account settings so that I can keep my information up to date. | 1) Connect to user database 2) Set up user settings page 3) Create settings button | Databases & User Authentication + Profiles | F | 2 | 1.5 | 1: Adam 100% 2: N/A 3: Adam 100%
43 | As an authorized user, I would like the application to not tell the person utilizing the “Forgot your password/account details” button if there exists an account with the specified email address, so that a hacker cannot trace my account through my email. | 1) Setup "Forgot your password/account details" button 2) Setup email has been sent page | Databases & User Authentication + Profiles | F | 2 | 1 | 1: Ashley: 100% 2: N/A
44 | As a business owner, I would like to modify my profile so that I can appeal and advertise to customers. | 1) Setup business profile page 2) Connect to user database 3) Modify business profile within database | Databases & User Authentication + Profiles | F | 3 | 1 | 1: N/A 2: Adam 50%, Liam 50% 3: N/A
45 | As a business owner, I would like to associate my email address with both a business account and a personal account so that I can maintain privacy. | 1) Connect to user database 2) Create new user with business setting enabled | Databases & User Authentication + Profiles | F | 2 | 1 | 1: Adam 50%, Liam 50% 2: N/A